## Sheet1
Risk | Potential/probability | Severity/impact | Risk value | Risk Mitigation | Risk prevention
All risks to project from sources, data, processes, people etc. | Chances of identified risk event occurring on a scale of say 1- 3 with 1 being not likely and 3 being very likely | Impact of risk event on project if the situation does happen. On a scale of 1-3 again with 1 being negligible impact and 3 being severe impact. | Potential * severity = risk value. Based on scale, risk value can be a number between 1-9. This leads to a final scale that tells us if the risk is negligible, light, serious or major | Steps or actions that can reduce the severity of the risk. Team can decide to skip having mitigation measures for risks below a certain risk value | Steps or actions that can reduce potential of the risk. Team can decide to skip having mitigation measures for risks below a certain risk value
Data Quality Risks
Inconsistenicies in data scraped from City of Calgary Community Profiles - multiple discrepencies in sums in multiple sections (e.g. total population does not equal total of males + females which does not equal total computed from individual age breakdowns) and mismatching totals used in different sections of profile (e.g. total private households used in income income is not the same as total private households used in ownership/rental section) | 3 | 1 - 2 (in most cases the noted error was 1% or 2%, most likely rounding error in the original data - this is neglibile and doesn't meaingfully impact the project outcomes a few instances where error was significantly greater is indicative of large error in source data which could cast doubt on veracity of entire data set and result in inaccurate results in the summary/output stage of the project) | 3 - 6 | Several mitigation options were discussed including 1) leave data as is 2) compute our own totals/percentages from constituents in profiles 3) purchase access to raw data source profiles were constructed from | Decision was made to compute our own totals and subsequent percentage fields using a sum of the constituent fields (when available) rather than accepting the calculated values shown in the City of Calgary Community Profiles. The assumption was made that these totals would be more accurate which may or may not be true.
Illogical data in City of Calgary Voter Turnout data - four instances of senior's homes having Enumerated Voters fewer than Votes Collected (i.e. voter turnout > 100%) | 3 | 1 | 3 | Several mitigation options were discussed including 1) remove all voter turnout data from senior's homes voting stations 2) null the four offending senior's homes data records 3) leave as is with voter turnout greater than 100% | Decision was made to null data from the four offending senior's homes as this left some useful data in the database but removed errors - there were many senior's homes with zero data points already so adding four more did not impress the team as problematic
Unknown inherent data errors in source data (i.e. we are assuming the voting results data published on City of Calgary website is free of all errors) | 2 | 1 - 3 (impact could range from negligible to severe depending on degree of error - a small 1%, as above, would not impact the project much - but a major error discovered in the source data could potentially ruin the validity of the entire project's results) | 2 -6 | Risks like this cannot be assertained so not mitigation steps could be discussed | Data source for voting results was simply assumed to be 100% accurate as there was no recourse available to us to confirm or refute this assumption
Transcription errors injected into data during conversion, compilation, and/or manipulation of master tables created in Excel | 3 | 1 (impact is again dependent on scale of error introduced - most will be minor and remedied during the QA process - there is, however, potential for major, undetected errors to be introduced which could make project outcomes invalid) | 3 | All data cleaning team members strove to do the best, most error-free work possible but errors are inevitable - Mitigation efforts include 1) Personal double checking and quick quality evaluations can be performed during each stage of work 2) comparitive calculations within the spreadsheet to catch egregious errors can be implemented | All efforts were made to limit errors but ultimately, it was primarily the QA team and DEV team who provided the final assurances of correctness on the data provided in the final master tables.
Calculation errors introduced into the master tables by performing our own calculations to mitigate other errors listed above | 1 | 1 (impact is again dependent on scale of error introduced - most will be minor and remedied during the QA process - there is, however, potential for major, undetected errors to be introduced which could make project outcomes invalid) | 1 | Care and observation taken to ensure such errors were not haphazardly added when calculations performed | All efforts were made to limit errors but ultimately, it was primarily the QA team and DEV team who provided the final assurances of correctness on the data provided in the final master tables.