## QA Lessons Learned
Project Management
Focus Area | Score |  |  |  |  | Successes | Failures | Recommendations
| 1 | 2 | 3 | 4 | 5
Project Planning |  |  |  | x |  | Timeline executed as planned | Not able to clearly convey what the team actually aims to do | Individual team timelines should be discussed amongst leads to better understand underlying tasks and efforts in work estimates
Resource Management |  |  |  | x |  | Each member of the team took accountability on assigned tasks
Change Control |  |  | x
Quality Control |  |  | x |  |  | Everyone tried to ensure quality of product | Limited knowledge on data and system (DB) | Test early and often
Status Reports | x | [5 empty] | Meetings were held and minutes were taken but were not rolled out as report to the group on a weekly basis | Weekly status report
Technical Management
Focus Area | Score |  |  |  |  | Successes | Failures | Recommendations
| 1 | 2 | 3 | 4 | 5
Requirements |  |  | x |  |  |  | No written document of High Level Requirement | School should have Business Requirement Document (BRD) that could be filled out by clients to be used as starting point in every Industry Project, it will be refined by the team with the client as Analyze meetings take place
Specification |  |  | x |  |  |  | Given no BRD, detailed design was delayed and always changing and so was test plan | BRD
Test Plan |  |  | x |  |  |  |  | BRD
Construction |  |  | x |  |  | Test Exercises done to prepare the team | Test Exercises did not cover System Test | Prepare team in all phases as necessary
Testing |  |  |  | x |  | Good understanding of what and how things are to be tested, everyone didn't hesitate to ask questions and help and suggested things that could help the team | Limited knowledge on data and system (DB) | More discussions within the team on system testing
Rollout | [7 empty] | n/a
Training |  |  | x |  |  | Test Exercises done to prepare the team | Test Exercises did not cover System Test | Prepare team in all phases as necessary
Documentation |  |  | x |  |  | Team collaborated in github | Team documents overwritten due to nonfamiliarity with github | Conduct an hour or two overview training of github
Human Factors
Focus Area | Score |  |  |  |  | Successes | Failures | Recommendations
| 1 | 2 | 3 | 4 | 5
Team Experience | x | [5 empty] | Lack of experience for roles taken | Share roles and responsibilities documents in overall project document for future reference of next cohorts
Interaction with Client |  |  | x |  |  |  | Given no base document, everyone had their own interpretation of what was discussed in meetings with the client | BRD
Interaction with Management
Management Support
Quality of Meetings |  |  | x |  |  | We were kept tracked by our meeting agendas | Overall team meetings - no minutes of the meeting | Review roles and responsibilities to ensure there is always someone to take minutes of the meeting for overall team meetings and send MOM to everyone
Overall
Focus Area | Score |  |  |  |  | Successes | Failures | Recommendations
| 1 | 2 | 3 | 4 | 5
Customer Satisfaction
Technical Success
Quality Product
Product Accepted
On Time |  |  | x |  |  |  | Takes most of the time of the week at some point | Maybe Industry project could be something that could be done by the class after all courses are done (maybe a month prior to practicum). This way, everyone is more knowledgeable on things, knows exactly what one is comfortable doing and more focused if only doing one thing.
Met Project Objectives
Met Business Objectives
Within Budget