## Sheet1
Risk | Potential/probability | Severity/impact | Risk value | Risk Mitigation | Risk prevention
Undefined USER Acceptance Criteria | 2 | 2 | 7 |  | QA to create test conditions to help USER refine and arrive at acceptance criteria
Schedule Delays | 2 | 2 | 7 |  | Increase test iteration, test by features
Requirement Changes | 2 | 2 | 7 |  | Tag test cases according to requirement for ease of reference for any change
Skills Defficiency | 2 | 2 | 5 | Seek help/assistance from advisors | Extensive research on database and visualization tools testing
Resource Availability | 1 | 3 |  | Assess need before hand | Define frequency of task status update
Poorly defined test cases for Phase 2 due to lack of knowledge of visualization tool | 3 | 3 |  | Deep business requirement understanding | Well defined USER acceptance test cases will help team to know what to test despite not much knowledge of platform
Limited Load testing | 3 | 3 |  |  | Calculate efficiency of complex database query for single USER
USER not able to perform actual acceptance test | 2 | 2 |  |  | QA team to be trained to test and document actual results of final product at USER's perspective